## GanttChart
Project Title | Egypt Future Educational Platform
Project Start |  | 2021-05-01 |  |  |  | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10
Show Week |  | 1 |  |  |  | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07 | 2021-05-08 | 2021-05-09 | 2021-05-10 | 2021-05-11 | 2021-05-12 | 2021-05-13 | 2021-05-14 | 2021-05-15 | 2021-05-16
Task | Assigned To | Progress | start | end | Days | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon2 | Tue3 | Wed4 | Thu5 | Fri6 | Sat7 | Sun8 | Mon9 | Tue10 | Wed11 | Thu12 | Fri13 | Sat14 | Sun15
User Specification |  | 100% | 2021-05-09 | 2021-05-18 | 10
Development Specification |  | 50% | 2021-05-18 | 2021-06-01 | 15
System Design |  | 50% | 2021-06-01 | 2021-06-25 | 25
Database Design |  |  | 2021-06-25 | 2021-07-19 | 25
Racks & server setup |  |  | 2021-07-19 | 2021-07-28 | 10
Datacenter setup |  |  | 2021-07-28 | 2021-08-11 | 15
Install router & switched and connection cables |  |  | 2021-08-11 | 2021-08-15 | 5
Configure DNS and Gateway |  |  | 2021-08-15 | 2021-08-29 | 15
Website Database And authorization implementation |  |  | 2021-07-19 | 2021-08-07 | 20
Website backend Testing & Integrations |  |  | 2021-08-07 | 2021-08-26 | 20
Prototype |  |  | 2021-07-19 | 2021-07-28 | 10
UI/UX Design |  |  | 2021-07-28 | 2021-08-26 | 30
Integrate Frontend with Backend and final testing |  |  | 2021-08-26 | 2021-09-25 | 31
Formulas:
end = [start]+[Days]-1
start = [end, row above]
start = MAX(E6,[end, row above])